## ContextDiagram
Context Diagram

## Assump-Oos
# | Assumptions | Client Remarks | Approx. Cost of Assumption in Man hours
We wull use the readymade theme.
QR scan from the web will take the picture of the QR code and submit it to the server for QR reading process. If photo will not be captured properly then this process needs to repeat until QR code read properly by the backend system. A third party library needs to use for QR code reading which needs to purchase by the client.
User must need to provide the permission to access the camera on their mobile.
We will perform QA/Testing on one of the platform/OS which is recommended by client.
We will perform functional and cross-browser UI testing on IE9, IE10, IE 11, Mozilla Firefox (latest two versions) and Google Chrome (latest two versions) as per bootstrap framework support.
Logo will be provided by the client in PSD format, if Radix will assist in Logo design then it will be charged Additionaly.
Any type of third party tool/API integration will be purchased by client and respective credentials will be provided to Radix to facilitate the development cycle.
For import we have considered the .csv file with the speicified column in the scope of work only.
For Reminder, windows schedular runs every day and send as per the date matches with the current date. Reminder date always be current date or future date. Reminder will not be configure for time and it will be as per the date only.
system will not have to consider or implement any validation which targets the physical location table mapping, table assignment or anything related to the arrangements at event place.
System will have 2 types of role (1) Event Organizor and (2) Admin Staff with predefined permission in the database. Superadmin will have full access to entire site.
Survey link will be sent next day of the event date automatically by the system without consideration whether actual event happened or not for active events.
System will work when the online connectivity is available. System will not work without internet.
# | Need From Client | Client Remarks | Approx. Cost of Assumption in Man hours
Third party libraries for QR scanner/Reading
Hosting server details.
# | Out of Scope | Client Remarks | Approx. Cost of Assumption in Man hours
Any Payment Processing
Implementation of Survey platform
Mobile application
Third Party Survey Integration
Front website or CMS pages.
Offline sync or working without internet
push notification

## Clarifications
Date | # | Radix Clarifications | Client Remarks | Date | # | Client Queries | Radix Remarks

## Featurelist
1 | Stakeholders (Use Case)
No. | Stakeholders | Activities of Stackholders
Event Organiser
Admin
Admin Staff
2 | Scope of Work
No. | Title/Module | Description | Efforts | Milestone
Event Organisers
1.1 | Authentications | Event Organisers will be able to login to the system using the valid credentials as passed by the admin | 1 | 1
| Event management |  | 4 | 1
|  | Add Event: Admin will be able to create event and add details Standard system Reminders are set before the date of the event |  | 1
|  | View List: Admin will be able to view the list and details of the events added |  | 1
|  | Edit: Admin will be able to make changes to the information of the event added |  | 1
|  | Delete: Admin will also be able to remove the event added. This will also remove the reminders set respective to the event |  | 1
| Reminder | Set Reminder: Admin will be able to set reminders for specific date and time prior to the date and time of the event. | 0 | 1
|  | System will show reminder notification to the admin showing the event name, date and time. | 1 | 1
| Email Management | Send Email / SMS Blast: Admin will be able to send the system generated QR Code to all the guest users of the selected event. SMS will contains the QR code link. | 0 | 1 | I am not sure SMS can contain the QR code.
|  | Note: Standard email template to be considered |  | 1
|  | Email for Survey: After the event, the system will send an email with the survey form link This will be a scheduled email sending. The system will read the URL entered at the time of importing guest database and will automatically send the email to all the attendees after the event time has been crossed | 4 | 1
1.2 | Guest Database | Import CSV: Event Organisers will be able to select their respective event and import guest database in a pre-defined format with pre-decided fields. | 2 | 1
|  | The details will include: Number of guests, Names Table Number Contact Number Lucky draw number Note: There can be multiple guests against single table number Based on the guest details entered, the system will generate a QR Code. |  | 1
|  | Along with the guest database, the event organiser will also be able to upload the URL for the survey that is to be mailed to the attendees of the events. | 6 | 1
1.3 | Report | • Number and List of Guests ( Invited / attended / absent) • Manually Registered Guests vs Scanned | 4 | 2
Admin
Admin will be able to perform all the event organisers functions + have a different dashboard and reports section. The tasks of Event management, importing guest database and setting reminders, sending email blasts will be done by
2.1 | Authentications | Admin will be able to login to the system using the valid credentials | 8 | 1
2.2 | User Management | Admin staff and Event Organisers: Admin will be able to create and manage admin staff accounts. The login credentials as set by the admin will be externally passed to the admin staff. | 32 | 1
|  | Automatic Notification: Users will receive notification for the URL and login credentials | 4 | 1
2.3 | Event management | Add Event: Admin will be able to create event and add details Standard system Reminders are set before the date of the event Events will not appear in the drop down list after the event date has passed | 10 | 1
|  | View List: Admin will be able to view the list and details of the events added | 8 | 1
|  | Edit: Admin will be able to make changes to the information of the event added | 6 | 1
|  | Delete: Admin will also be able to remove the event added. This will also remove the reminders set respective to the event | 4 | 1
| Reminder | Set Reminder: Admin will be able to set reminders for specific date and time prior to the date and time of the event. | 24 | 1
|  | System will show reminder notification to the admin showing the event name, date and time. | 10 | 1
| Guest Database | Import CSV: Event Organisers will be able to import guest database in a pre-defined format with pre-decided fields. | 32 | 1
|  | The details will include: Number of guests, Names Table Number Contact Number Lucky Draw Number Note: There can be multiple guests against single table number Based on the guest details entered, the system will generate a QR Code. |  | 1
2.4 | Email Management | Send Email / SMS Blast: Admin will be able to send the system generated QR Code to all the guest users of the selected event | 24 | 1
Note: Standard email template to be considered
2.5 | Report | • Number of Events (Completed / Upcoming) • Number of Guests ( Invited / attended / absent) • Manually Registered Guests vs Scanned • Registeres Event Organisers | 24 | 2
Admin Staff
3.1 | Login | Admin staff will be able to login to the portal using the login credentials passed by the admin | 1 | 1
3.2 | Attendance | QR Code Scanner: The web application will have a QR Code scanner integrated to scan the QR code in the guest emails or the sms. This will help them mark the attendance at the time of the event. Note: Multiple Admin staff users will be able to select and add details to a single event at a time but the database will be centrally updated allowing no duplicate information capturing | 40 | 2
|  | Mark Manual Attendance: Admin staff will be able to manually mark the attendance of the guest users in case they do not have the QR Code email with them | 12 | 2 | Please split this into two sections
| Add Guest | Add guest: At the time of event attendance, if there are users who doesn't have a QR code to scan, the admin staff will be able to manually enter their details into the system. Details to be added can be: Name, Email ID, Contact Number, Table Number, Lucky Draw Number will be added. | 20 | 2 | Lucky draw number is available here but not in the import CSV, I think it should be
3.3 | Email Management | Email for Table number: As soon as the QR Code is scanned or attendance is added manually, the system sends Email / SMS to the attendees telling them about their table number and lucky draw number | 16 | 2 | If User didn’t received the email or SMS, there should be a provision which shows the table number assigned.
|  | Email for Survey: After the event, the system will send an email with the survey form link. | 20 | 2
| Event Details | Admin staff can able to view the Particular event details which should show 1) Attendes Name 2) Attendes Email 3) Attendes Phone No. 4) Attendes Table No. | 12 | 2
| Total Internal hours |  | 329
3 | Designing Features
No. | Title | Description | Efforts
| Theme Integration | Design team will prepare the PSD for approval and then integrate the readymade theme into the site. | 40
| Total Internal hours |  | 40
| No. | Software Stages
| 1 | Requirement Study/ Understanding and team alignment | 16
| 2 | Architecture Setup | 8
| 3 | Designing (PSD + HTML) - Approx 5/7 Unique screens. | 40
| 4 | Database Designing | 8
| 5 | Development | 329
| 6 | QA Testing | 40
| 7 | Deployment | 16
| 8 | Project Management | 40
|  | Total Person Hours | 497
4 | Deliverables:
No. | Title | Description | Efforts
1 | Working Application | It will be Provided by Default
2 | User/Help Manual | It will not be provided. Efforts will be estimated separately if client need it with brief overview | 0
3 | Any kind of System Design Document (FRS, SRS, URS, FDS) | It will not be provided. Efforts will be estimated separately if client need it with brief overview | 0
4 | Use Cases/Test Cases | It will not be provided. Efforts will be estimated separately if client need it with brief overview | 0
5 | Demo/Training | One time demo/training will be given for overall system understanding. Efforts will be estimated separately if client need additional training session for system understanding. | 0
6 | Hosting Support | We will be responsible to make deployment on provided shared/dedicated/cloud hosting only. Any support or consulting with hosting provider will be charged separately as time & material basis | 0
7 | Warranty | 1 Month Support for UAT Issues and working System | 0
8 | Legacy Data migration | We have not considered legacy data migration in current scope. Efforts will be estimated separately if client need it with brief overview | 0
| Total Internal hours |  | 0
Note on C70: kpuser: Only those hours which should be from Designing Team

## Technology
Project Name | WDC_EventManagementSystem
Task ID | 150498
Client Name | Samson Sang
Project Scope Brief | The project is about building an event management system to send invitation to the guests and later mark attendance at the event venue.
Features Listing By | Deshana Shah
Development Efforts/Estimation By | Dharmendra Solanki
Development Environment(Website) | Asp.Net Core 2 , Bootstrap 4, Angular, Entity Framework Core, Typescript, SQL Server 2017
Deployment Environment | Windows Server, IIS
Third Party Integration Details | QR Code Scanner

## Planning (hidden)
Public Holiday
| Project Team | No | Remark
Project Manager*
Sr. Developer*
Designer*
Milestones | Module/Activity | Team | Hours Estimated | Total Weeks Required
Milestone 1 | Design & Theme Setup
QA & UAT
Staging
Milestone 2
Staging Deployment & Demo
Milestone 3
Live Deployment & Demo
Documentation/Help Manual
| Total |  | 0 | 0
Note: | Above project plan is tentative as per the present available information and planning. It will be revised after completion of requirement gathering & requirement analysis.
Note on B3: Deepa Patel: Number of developers/manager/QA/Designed considered for the development. Here is just example so update as required

## Project Planning
Public Holiday
Project Execution Progress
| Project Team | No | Remark
| Project Manager* | 1
| Sr. Developer* | 2
| Designer* | 1
| QA | 1
| BA | 1
| Client | 1
181
Mobile Planning | [12 empty] | 148
Milestones | Module/Activity | Team | Hours Estimated ( 2 Dev + 1 QA + Proj manager) | Total Weeks Required | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Milestone 1 (W1-W4) | Requirement Understanding |  | 16 | bar: W1
| Designing |  | 40 | bar: W1
| Architecture Setup |  | 8 | bar: W1
| Database Designing |  | 8 | bar: W1
| Project Planning |  | 40 | bar: W1
| Development |  | 181
Event Organizor -Event management -Reminder -Email Management -Guest Database Admin Authentications -User Management -Event management -Reminder -Guest Database -Email Management Admin Staff -Login | bar: W1 to W3
QA | bar: W3 to W4
Client UAT | bar: W4 to W5
Milestone 2 (W4-W7) | Development
Event Organizor -Report Admin -Report Event Staff -Attendance -Add Guest -Email Management -Event Details | bar: W4 to W6
QA | bar: W6 to W7
Client UAT
Milestone (W8) | Client UAT | bar: W7 to W8
Note: | Above project plan is tentative as per the present available information and planning. It will be revised after completion of requirement gathering & requirement analysis.
Note on B5: Deepa Patel: Number of developers/manager/QA/Designed considered for the development. Here is just example so update as required